## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Week 1 | Week 3 | Week 4 | Week 5 | Sprint Review
As a general user I can access testimonials in order to see what others think about the product and leave a testimonial myself | Task 1 | Andre | Complete | 20 | 2 | 1 | 3 | 0 | 0
| Task 2 | Andre | Complete | 10 | 1 | 2 | 0 | 0 | 0
| Task 3 | Jacob | Complete | 25 | 20 | 15 | 10 | 10 | 0
As a guest I need to contact the administrator so that I can receive assistance when I need it | Task 4 | Jacob | Complete | 25 | 10 | 15 | 20 | 15 | 0
| Task 5 | David | Complete | 25 | 16 | 13 | 10 | 0 | 0
| Task 6 | Alex | Complete | 15 | 5 | 14 | 10 | 12 | 0
| Task 7 | Krupesh | Complete | 15 | 10 | 10 | 15 | 0 | 0
As a user I want the ability to see the shapes I create in a window. The shapes will have an ID and the window will be 1000 by 500 pixels. | Task 8 | Anthony | Complete | 20 | 16 | 12 | 10 | 8 | 0
| Total |  |  | 155 | 80 | 82 | 78 | 45 | 0
As a user I want the program to display shapes based on a file
As an administrator, I want to move the shapes and text in my rendering area using a move shape form
As an administrator I want to Add or remove a shape from the rendering area
As a user I want to able to see the list of shapes that I created. I would like to see two seperate listing reports: one that lists the shapes by area, and one that lists the shapes by perimeter.
As a <user> I <need> <to be able to save all changes between executions>