## Sprint1
Product Backlog Item	Task	Volunteer	Status	Original Estimate	Week 1	Week 3	Week 4	Week 5	Sprint Review
As a general user I can access testimonials in order to see what others think about the product and leave a testimonial myself	Task 1	Andre	Complete	20	2	1	3	0	0
	Task 2	Andre	Complete	10	1	2	0	0	0
	Task 3	Jacob	Complete	25	20	15	10	10	0
As a guest I need to contact the administrator so that I can receive assistance when I need it	Task 4	Jacob	Complete	25	10	15	20	15	0
	Task 5	David	Complete	25	16	13	10	0	0
	Task 6	Alex	Complete	15	5	14	10	12	0
	Task 7	Krupesh	Complete	15	10	10	15	0	0
As a user I want the ability to see the shapes I create in a window. The shapes will have an ID and the window will be 1000 by 500 pixels.	Task 8	Anthony	Complete	20	16	12	10	8	0
	Total			155	80	82	78	45	0

As a user I want the program to display shapes based on a file

As an administrator, I want to move the shapes and text in my rendering area using a move shape form

As an administrator I want to Add or remove a shape from the rendering area

As a user I want to able to see the list of shapes that I created. I would like to see two seperate listing reports: one that lists the shapes by area, and one that lists the shapes by perimeter.

As a <user> I <need> <to be able to save all changes between executions>